## Sheet1
PROJECT | CONTRACTOR | CO# | CURRENT CONTRACT AMOUNT |  | CHANGE | REVISED AMOUNT | EXPLANATION (see attached) | SALES TAX SAVINGS * | **
SUMMARY OF FACILITIES CHANGE ORDERS PRESENTED FOR APPROVAL AND/OR RATIFICATION AT THE OCTOBER 3, 2006 SCHOOL BOARD MEETING
Bay Haven 2006 Renovations | Jon F. Swift, Inc. | 1 | 249953.79 | + | 71063.02 | 321016.81 | Paint doors, hardware & wheelcahir lift. |  | R | r
Bay Haven 2006 Renovations | Jon F. Swift, Inc. | 2 | 321016.81 | + | 25572.88 | 346589.69 | Add for second top coat of paint on all stucco and masonry surfaces and replacing expansion joint. |  | R
Venice High Parking Area Improvements | Willis A Smith | 3 | 863849 | - | -19254 | 844595 | Delete site signage. |  | R
Venice High Parking Area Improvements | Willis A Smith | 6 | 857902 | - | -33786 | 824116 | Reconcilliation of Allowances |  | R
Pine View Site Improvements` | Jon F. Swift, Inc. | 3 | 374743.92 | + | 2686.84 | 350430.76 | Add sidewalk at Custodial shed. |  | R
|  |  | Total additions |  | 46282.74
**A=Approval; R=Ratification
[6 empty] | 0 | ADD
[6 empty] | 0 | SUBTRACT
[6 empty] | 0 | SUBTRACT