## Sheet1
PROJECT | CONTRACTOR | CO# | CURRENT CONTRACT AMOUNT |  | CHANGE | REVISED AMOUNT | EXPLANATION (see attached) | SALES TAX SAVINGS * | **
SUMMARY OF FACILITIES CHANGE ORDERS PRESENTED FOR APPROVAL AND/OR RATIFICATION AT THE SEPTEMBER 5, 2006 SCHOOL BOARD MEETING
Pine View Site Improvements | Jon F. Swift Inc. | 1 | 207459.23 | + | 3464.17 | 210923.4 | Relocate sidewalk and footings at South parking area. |  | R | r
SHS Bldg #14 Interior Renovation | McIntyre, Ellwell & Stammer GC, Inc. | 1 | 769102 | + | 14806 | 783908 | Add receptacles, boxes, raceways, switches and quad data outlets in 21 classrooms.
Tuttle Repaint/Roof Drain Repair | W.G. Mills Inc. | 2 | 162812 | + | 4367 | 167179 | Prep and paint both sides of all exterior hollow metal doors and frames.
|  |  | Total additions |  | 22637.17
**A=Approval; R=Ratification
[6 empty] | 0 | ADD
[6 empty] | 0 | SUBTRACT
[6 empty] | 0 | SUBTRACT